## Baseline
SOW C365043 — Team Profile ¦ 4.5 days/week ¦ 20 Jul – 19 Dec 2026 ¦ Baseline (v7 DRAFT)
[7 empty] | Mobilisation |  |  |  | Implementation | [15 empty] | Transition
Role | Lvl | PHM Contract Role | SFIA | Notes | SOW Milestone(s) | Supplier | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22
■ 1.0 FTE <1.0 FTE □ not active ¦ Kainos QB CGI | [6 empty] | 20 Jul | 27 Jul | 03 Aug | 10 Aug | 17 Aug | 24 Aug | 31 Aug | 07 Sep | 14 Sep | 21 Sep | 28 Sep | 05 Oct | 12 Oct | 19 Oct | 26 Oct | 02 Nov | 09 Nov | 16 Nov | 23 Nov | 30 Nov | 07 Dec | 14 Dec
Core
W0 - Governance Team
Head of Product | 0 | Lead Product Manager * | 6 | Day-to-day prgramme lead, governance and ops | MS00; PDG packs; TDA coord (all wkstrms) | QB | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Principal Delivery Manager | 1 | Programme Delivery Manager | 6 | Day-to-day prgramme lead, governance and ops | MS00; PDG packs; TDA coord (all wkstrms) | Kainos | bar: Mobilisation W1 to Transition W22
Security Arch/IG | 2 | Lead Security Architect | 5 | Governance and compliance, DPIAs etc. | MS00; DPIAs × 7; DGG submissions | Kainos | 1 | 1 | 1 | 1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
QA Lead | 2 | Lead Test Engineer | 6 | Overall test principles, strategy and assurance | All milestones — quality assurance | CGI | bar: Mobilisation W1 to Transition W22
Portfolio Lead | 2 | Lead Product Manager * | 5 | WP-QB1 Portfolio Management and Benefits Management | MS00; PDG; benefits (all milestones) | QB | bar: Mobilisation W1 to Transition W22
CSO | 2 | Delivery Manager | 5 | Clinical Safety Governance Placeholder | TBD — Clinical Safety scope (W2, W6) | ? | bar: Mobilisation W1 to Transition W22
CSO | 2 | Delivery Manager | 5 | Clinical Safety Governance Placeholder | TBD — Clinical Safety scope (W2, W6) | ? | bar: Mobilisation W1 to Transition W22
Design Pod
SD | 2 | Lead Service Designer * | 6 | WP-QB5 | MS08; design support W2–W7 | QB | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Prod Mgr | 4 | Lead Product Manager * | 4 | WP-QB5 | MS03.1; MS08; user research support | QB | bar: Mobilisation W1 to Transition W22
Translator | 4 | Service Designer * | 4 | WP-QB5 | MS03.1; MS08; user research support | QB | bar: Mobilisation W1 to Transition W22
Centralised Front-End Engineering Support (React)
React FE Dev | 3 | Lead Software Developer | 5 | Augment other Workstreams and W7 | MS08 (W7 build) | Kainos | bar: Mobilisation W1 to Transition W22
Track A
W1, 3-5 Leadership of Track A Work
Prod Mgr | 2 | Lead Product Manager | 5 | We need product input into FDP deliverables | MS02.1–02.2; MS04.1–04.3; MS05.01–05.03; MS06.1–06.4 | Kainos | bar: Mobilisation W1 to Transition W22
Solution Architect - FDP | 2 | Senior Data Architect | 6 | W1, 3-5 Focus | MS02.1; MS04.1; MS05.01; MS06.1 (W1/3/4/5 arch) | Kainos | bar: Mobilisation W1 to Transition W22
W1 Delivery - Tableau Reporting Migration
BA | 4 | Business Analyst | 4 | Prioritisation of dashboards and analysis | MS02.1; MS02.2 | CGI | bar: Mobilisation W1 to Transition W22
FDE | 4 | Senior Data Engineer | 4 |  | MS02.1; MS02.2 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS02.1; MS02.2 | Kainos | bar: Mobilisation W1 to Transition W22
W2 Delivery - MHA
Product/Delivery Mgr | 2 | Lead Service Designer * | 6 | WP-QB3 | MS03.1; MS03.2 | QB | bar: Mobilisation W1 to Transition W22
Service/UX Designer | 3 | Service Designer * | 4 | WP-QB3 | MS03.1; MS03.2 | QB | bar: Mobilisation W1 to Transition W22
W3 Delivery - Workforce and Job Planning
FDE | 4 | Senior Data Engineer | 4 |  | MS04.1; MS04.2; MS04.3 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 4 | Senior Data Engineer | 4 |  | MS04.1; MS04.2; MS04.3 | Kainos | bar: Mobilisation W1 to Transition W22
Integration Engr | 4 | Lead Software Developer | 5 |  |  | CGI | bar: Mobilisation W1 to Transition W22
QA | 5 | Test Engineer | 4 |  | MS04.2; MS04.3 | Kainos | bar: Mobilisation W1 to Transition W22
W4 Delivery - Suppliy Chain: Loan Equipment
FDE | 4 | Senior Data Engineer | 4 |  | MS05.01; MS05.02; MS05.03 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 6 | Data Engineer | 3 |  | MS05.01; MS05.02; MS05.03 | Kainos | bar: Mobilisation W1 to Transition W22
QA | 5 | Test Engineer | 4 |  | MS05.01; MS05.02; MS05.03 | CGI | bar: Mobilisation W1 to Transition W22
W5 Delivery - Supply Chain: Inventory360
FDE | 3 | Lead Data Engineer | 5 | Risk as unknown | MS06.1; MS06.2; MS06.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 4 | Senior Data Engineer | 4 |  | MS06.1; MS06.2; MS06.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS02.1; MS02.2 | CGI | bar: Mobilisation W1 to Transition W22
W7 Delivery - FDP Homepage
Content Designer | 3 | Content Designer | 4 |  | MS08 | CGI | bar: Mobilisation W1 to Transition W22
React FE Dev | 4 | Senior Software Developr | 4 |  | MS08 | CGI | bar: Mobilisation W1 to Transition W22
Track B
W6 Leadership
DM | 2 | Lead Service Designer * | 6 |  | M07.0; MS07.1-3.1–07.1-3.4 | QB | bar: Mobilisation W1 to Transition W22
Solution Architect - FDP | 2 | Senior Data Architect | 6 | W6 Focus | M07.0; MS07.1-3.1–07.1-3.4 (W6 arch) | CGI | bar: Mobilisation W1 to Transition W22
Data Scientist | 2 | Senior Data Scientist * | 5 | WP-QB2 Modelling & Analytics Defn. | M07.0; MS07.1-3.1–07.1-3.4 | QB | bar: Mobilisation W1 to Transition W22
W6a Delivery
FDE | 4 | Senior Data Engineer | 4 |  | MS07.1.1; MS07.1.2; MS07.1.3; MS07.1.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS07.1.1; MS07.1.2; MS07.1.3; MS07.1.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS02.1; MS02.2 | CGI | bar: Mobilisation W1 to Transition W22
W6b Delivery
FDE | 4 | Senior Data Engineer | 4 |  | MS07.2.1; MS07.2.2; MS07.2.3; MS07.2.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS07.2.1; MS07.2.2; MS07.2.3; MS07.2.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS02.1; MS02.2 | CGI | bar: Mobilisation W1 to Transition W22
W6c Delivery
FDE | 4 | Senior Data Engineer | 4 |  | MS07.3.1; MS07.3.2; MS07.3.3; MS07.3.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS07.3.1; MS07.3.2; MS07.3.3; MS07.3.4 | Kainos | bar: Mobilisation W1 to Transition W22
FDE | 5 | Data Engineer | 3 |  | MS02.1; MS02.2 | CGI | bar: Mobilisation W1 to Transition W22
TOTAL

## Workshare
CGI | 555239.25 | 21.28%
QB | 775024.49 | 29.71%
Kainos | 1278648.24 | 49.01%
Other | 75368.7
Sub-Total | 2684280.68

## QB Profile
[8 empty] | Mobilisation |  |  |  | Implementation | [15 empty] | Transition
# | Role | Lvl | PHM Contract Role | SFIA | Notes | SOW Milestone(s) | Weighted Rate | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | FTE Wks | Days | Forecast (£) | Cost Rate/day | Forecasted Cost
1 | Head of Product | 0 | Lead Product Manager * | 6 | Day-to-day prgramme lead, governance and ops | MS00; PDG packs; TDA coord (all wkstrms) | 1480.41 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 4.4 | 19.8 | 29312.118 | 1406.3895 | 27846.5121
5 | Portfolio Lead | 2 | Lead Product Manager * | 5 | WP-QB1 Portfolio Management and Benefits Management | MS00; PDG; benefits (all milestones) | 1480.41 | [22 empty] | 22 | 99 | 146560.59 | 1406.3895 | 139232.5605 | bar: Mobilisation W1 to Transition W22
8 | SD | 2 | Lead Service Designer * | 6 | WP-QB5 | MS08; design support W2–W7 | 1430.84 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 16 | 72 | 103020.48 | 1359.298 | 97869.456
9 | Prod Mgr | 4 | Lead Product Manager * | 4 | WP-QB5 | MS03.1; MS08; user research support | 1480.41 | [22 empty] | 12 | 54 | 79942.14 | 1406.3895 | 75945.033 | bar: Mobilisation W1 to Implementation W12
10 | Translator | 4 | Service Designer * | 4 | WP-QB5 | MS03.1; MS08; user research support | 1210.52 | [22 empty] | 12 | 54 | 65368.08 | 1149.994 | 62099.676 | bar: Mobilisation W1 to Implementation W12
17 | Product/Delivery Mgr | 2 | Lead Service Designer * | 6 | WP-QB3 | MS03.1; MS03.2 | 1430.84 | [22 empty] | 12 | 54 | 77265.36 | 1359.298 | 73402.092 | bar: Mobilisation W1 to Implementation W12
18 | Service/UX Designer | 3 | Service Designer * | 4 | WP-QB3 | MS03.1; MS03.2 | 1210.52 | [22 empty] | 12 | 54 | 65368.08 | 1149.994 | 62099.676 | bar: Mobilisation W1 to Implementation W12
31 | DM | 2 | Lead Service Designer * | 6 |  | M07.0; MS07.1-3.1–07.1-3.4 | 1430.84 | [22 empty] | 18 | 81 | 115898.04 | 1359.298 | 110103.138 | bar: Mobilisation W1 to Transition W22
33 | Data Scientist | 2 | Senior Data Scientist * | 5 | WP-QB2 Modelling & Analytics Defn. | M07.0; MS07.1-3.1–07.1-3.4 | 1281.8 | [22 empty] | 16 | 72 | 92289.6 | 1217.71 | 87675.12 | bar: Mobilisation W1 to Transition W22
| TOTAL | [29 empty] | 559.8 | 775024.488 |  | 736273.2636

## Order Form Table
Role | PHM Contract Role | SFIA | SOW Milestone(s) | Days | Cost Rate/day | Forecasted Cost
Head of Product | Lead Product Manager * | 6 | MS00; PDG packs; TDA coord (all wkstrms) | 19.8 | 1406.3895 | 27846.5121
Portfolio Lead | Lead Product Manager * | 5 | MS00; PDG; benefits (all milestones) | 99 | 1406.3895 | 139232.5605
SD | Lead Service Designer * | 6 | MS08; design support W2–W7 | 72 | 1359.298 | 97869.456
Prod Mgr | Lead Product Manager * | 4 | MS03.1; MS08; user research support | 54 | 1406.3895 | 75945.033
Translator | Service Designer * | 4 | MS03.1; MS08; user research support | 54 | 1149.994 | 62099.676
Product/Delivery Mgr | Lead Service Designer * | 6 | MS03.1; MS03.2 | 54 | 1359.298 | 73402.092
Service/UX Designer | Service Designer * | 4 | MS03.1; MS03.2 | 54 | 1149.994 | 62099.676
DM | Lead Service Designer * | 6 | M07.0; MS07.1-3.1–07.1-3.4 | 81 | 1359.298 | 110103.138
Data Scientist | Senior Data Scientist * | 5 | M07.0; MS07.1-3.1–07.1-3.4 | 72 | 1217.71 | 87675.12
TOTAL |  |  |  | 559.8 |  | 736273.2636